## Read Me
To use the template
0 | File -> Make a copy, and share it among the members & the instructor (yan.chen01@sjsu.edu)
1 | In Members, enter member names & email for each role
(for 3-people group, delete 1 row of programmer)
2 | In Backlog, enter group number (members will be auto-filled in based on what you entered in 1)
Then document each task as a row:
| 2.1) | Choose milestone number
| 2.2) | Describe the task (method name, class name, etc.)
| 2.3) | Choose the member who's responsible for the task
| 2.4) | Choose the status
| 2.5) | For started (In Progress) tasks, enter the start date
| 2.6) | For Completed tasks, enter the end date
| 2.7) | Enter any additional notes
Color Codes (auto)
Red background: |  | Error
Red text: |  | Urgent task (due soon or blocking other tasks)
Grey text: |  | Completed
The last submission should have NO red background (no error) and all taskes should be in grey (all completed)
Possible Errors
| 1 & 2 | Missing group number or group members
| 2.5) | Missing start date for an In Progress or Completed task
OR Having start date for a Not Started task
| 2.6) | Missing end date for a Completed task
OR Having end date for an uncompleted task

## Members
Role | Name | Email
UI Designer | Sri Kothapalli | srinithya.kothapalli@sjsu.edu
Programmer | Alex S | Althex123@gmail.com
Programmer | Vasudev Vinod | vasudev.vinod@sjsu.edu
Tester | Andy Martin Valencia | andy.martinvalencia@sjsu.edu

## Backlog
Group 1
Members: | Sri Kothapalli, Alex S , Vasudev Vinod, Andy Martin Valencia
Milestone # | Task | Member | Status | Start Date | End Date | Comments
Milestone 2 | Implement occursOn | Alex S | Completed | 2024-10-10 | 2024-10-10
Milestone 2 | Test occursOn | Andy Martin Valencia | Completed | 2024-10-10 | 2024-10-10
Milestone 2 | Finish Backlog | Vasudev Vinod | Completed | 2024-10-10 | 2024-10-10
Milestone 2 | JUnit Testing | Andy Martin Valencia | Completed | 2024-10-10 | 2024-10-10
Milestone 2 | occursOn Method | Sri Kothapalli | Completed | 2024-10-10 | 2024-10-10
Milestone 2 | localDate Method | Alex S | Completed | 2024-10-10 | 2024-10-10
Milestone 3 | Update Appointment Class | Sri Kothapalli | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | OnetimeAppointment subclass | Sri Kothapalli | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | DailyAppointment subclass | Sri Kothapalli | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | MonthlyAppointment subclass | Sri Kothapalli | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | Implement OccursOn | Sri Kothapalli | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | Implement toString | Sri Kothapalli | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | Update Backlog | Sri Kothapalli | Completed | 2024-11-04 | 2024-11-04
Milestone 3 | Update Appointment Class | Alex S | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | OnetimeAppointment subclass | Alex S | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | DailyAppointment subclass | Alex S | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | MonthlyAppointment subclass | Alex S | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | Implement OccursOn | Alex S | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | Implement equals | Alex S | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | Update Backlog | Alex S | Completed | 2024-11-04 | 2024-11-04
Milestone 3 | Transfer code collaborated on to IntelliJ | Andy Martin Valencia | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | Complete JUnit Testing for all implementations | Andy Martin Valencia | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | Update Backlog | Andy Martin Valencia | Completed | 2024-11-04 | 2024-11-04
Milestone 3 | Update Appointment Class | Vasudev Vinod | Completed | 2024-10-30 | 2024-10-30
Milestone 3 | Update Backlog | Vasudev Vinod | Completed | 2024-11-04 | 2024-11-04
Milestone 3 | Submit Milestone 3 (CANVAS) | Sri Kothapalli | Completed | 2024-11-04 | 2024-11-04
Milestone 3 | Make Appointments Comparable | Alex S | Completed | 2024-11-04 | 2024-11-25
Milestone 4 | Create AppointmentManager | Vasudev Vinod | Completed | 2024-11-22 | 2024-11-25
Milestone 4 | Implement .add() | Vasudev Vinod | Completed | 2024-11-22 | 2024-11-25
Milestone 4 | Implement .delete() | Vasudev Vinod | Completed | 2024-11-22 | 2024-11-25
Milestone 4 | Implement .update() | Sri Kothapalli | Completed | 2024-11-22 | 2024-11-25
Milestone 4 | Implement getAppointmentsOn | Sri Kothapalli | Completed | 2024-11-22 | 2024-11-25
Milestone 4 | JUnit Testing | Andy Martin Valencia | Completed | 2024-11-22 | 2024-11-25
Milestone 4 | Create UI | Sri Kothapalli | Completed | 2024-11-22 | 2024-11-25
Milestone 4 | Submite Milestone 4 | Vasudev Vinod | Completed | 2024-11-25 | 2024-11-25